## WBS_WorkPlace
Work Breakdown Structure
ID | Task | TASK ID | Status | Effort Hours | Start Date | Planned Completion | Estimate to Completion | Resource
1 | Requirements Analysis | TASK 1 | Completed | 4 | 2023-08-13 | 2023-08-13 | 2023-08-13 | Parneet
2 | Test Case and Test data Creation | TASK2 | Completed | 8 | 2023-08-14 | 2023-08-15 | 2023-08-15 | Parneet
3 | Creation of final test report | TASK3 | Completed | 3 | 2023-08-15 | 2023-08-15 | 2023-08-15 | Parneet
Note on C3: Options are: Open Closed
Note on D3: Options are: Open Closed